## Sheet1
wp | activity | start_date | end_date
Data team | Data collection | 2020-09-01 | 2020-09-10
Data team | Data processing | 2020-09-08 | 2020-09-14
Data team | Reporting | 2020-09-14 | 2020-09-16
Data team | Data visualisation | 2020-10-23 | 2020-10-30
Investigative team | Fieldwork | 2020-09-05 | 2020-09-15
Investigative team | Fieldwork | 2020-10-10 | 2020-10-20
Investigative team | Writing | 2020-10-21 | 2020-10-31
Social media team | Draft outputs | 2020-10-25 | 2020-10-28
Social media team | Active promo | 2020-10-31 | 2020-12-15